## mIGRATIONS
hide | notify Michelle | Location | Pew and time | date for migration | FER | notes | wfmt cp Job | WFMT ref | install job ref | Install job resourced | coop job no | Coop job Y/N | Notes | complete | moved |  | planned | cables in and complete | due for completion | notes or issues
hide | to notify | Faraday | PW546656 | 2021-05-18 | FER 4 | PEW to migrate CP’s from FER 4 faraday to the Nokia FER’s Zen Internet Ltd BBCH01629327 POID01629326 WMEP00000414 - WMEP00000415 BGP Peers 82.71.176.18 - 82.71.176.22 Kingston Communications BBCH01606424 POID01606425 WMEP00000416 - WMEP00000417 BGP Peer IP's 82.153.0.145 - 82.153.0.149 Claranet BBCH15087982 POID15087984 WMEP00000880 - WMEP00000880 BGP Peer IP's 195.8.68.10 - 195.8.68.14 |  |  | PREP Estimate:- WAWCCD5W |  | WAWCCE2V | [8 empty] | new cables on site
hide | Michelle | Faraday | PW546657 | 2021-07-06 | FER 5 | "Service impacting Change being manually notified by enterprise, contact Mark Haley for detail" Following successful completion of FOA migrations we will migrate remaining services from Cisco FER to the Nokia FER: Cisco FER to be migrated is fer-cis5.l-far BT GLOBAL SERVICES (NHS-N3) BBCH12241301 POID12241300 WMEP00000616 - WMEP00000617 BGP Peers 81.147.220.130 - 81.147.220.134 TELEFONICA O2 UK LIMITED BBCH12353041 POID12353042 WMEP00000636 - WMEP00000637 PGP Peers 46.233.123.66 - 46.233.123.70 TELEFONICA O2 UK LIMITED BBCH05677257 POID05677259 WMEP00000514 - WMEP00000515 BGP PEERS 87.194.4.34 - 87.194.4.38 |  |  | PREP ESTIMATE: WAWCFA0U |  | OOH Estimate :-WAWCFA4Y | [8 empty] | Order Reference :-310375 Delivered By 17/05/2021
| to note | colindale | PW544883 | 2021-05-26 | FER 2 | Cisco FER to be migrated is fer-cis2.l-nws. Andrews and Arnold POID15219791 BBCH15219790 VLAN's 1066 and 1067 BGP Peers 90.155.64.50 and 90.155.64.54 Zen POID15224584 BBCH15224583 VLAN's 1082 and 1083 BGP Peers 82.71.176.81 and 82.71.176.85 | awaiting | awaiting(Not Done) | • NIMS WAVWNK2A /51181398:- PRE-CABLING PREP FOR FER 2 PW544883 CROL • NIMS 51181402 WAVWNK4C – OOH Support for FER Replacement Cisco FER2 to Nokia 10G PW544883 Cabling | awaiting | • ASC Order Number:- FS0500682:-Requested Delivery Date: 08-03-2021 | awaiting | awaiting | awaiting |  |  | yes |  |  | priority 2
| to note | colindale | PW542677 | 2021-06-08 | FER 4 | Cisco FER to be migrated is fer-cis4.l-nws Murphx BBCH15026123 WMEP00000866 - WMEP00000867 BGP Peers 62.72.148.86 - 62.72.148.90 ICUK BBCH13032936 WMEP00000820 - WMEP00000821 BGP Peers 80.209.128.162 - 80.209.128.166 | NoCp Yet | awaiting(Not Done) | PREP ESTIMATE:-WAWA4H0P/51184524 and OOH Estimate :-WAWA4L2A/51184551 |  | PREP ESTIMATE:-WAWA4H0P/51184524 and OOH Estimate :-WAWA4L2A/51184551 | awaiting | awaiting | awaiting |  |  | no
hide | to notify | colindale | PW543115 | was 09/06/2021 reschedule | FER 4 | Cisco FER to be migrated is fer-cis4.l-nws WAVENET LTD BBCH15096008 POID15096010 WMEP00000888 WMEP00000889 BGP Peers 195.26.38.110 - 195.26.38.106 Zen BBCH12837898 POID12837899 WMEP00000750 WMEP00000751 BGP peers 82.71.176.9 - 82.71.176.13 | NoCp Yet | Not Planned Yet | PREP ESTIMATE:-WAWD449J and OOH Estimate :-WAWD457J |  |  |  | NA | n | moved from 21 Jan |  |  |  |  | ASC Order Reference :-315093 delivered in 3 working days 10/06/2020
michelle | to notify | colindale | PW544452 | 2021-06-15 | fer 3 | Cisco FER to be migrated is fer-cis3.l-nws Cable & Wireless UK POID04623295 BBCH04623294 WMEP00000490 - WMEP00000490 BGP Peers 87.74.20.33 - 87.74.20.37 BBCH15037651 WMEP00000878 - WMEP00000878 BGP Peers 87.74.215.45 - 87.74.20.45 Murphx POID12948106 BBCH12948105 WMEP00000794 - WMEP00000795 BGP Peers 62.72.148.78 - 62.72.148.82 Griffin POID01891861 BBCH01891860 WMEP00000458 - WMEP00000458 BGP Peers 79.121.251.222 - 79.121.251.226 Cerberus POID15361323 BBCH15361322 WMEP00000978 - WMEP00000979 BGP Peers 46.37.35.154 - 46.37.35.158 | awaiting | Not Planned Yet | PREP work: 51191119 WAWAWC9E | awaiting | OOH :51191122 WAWAWD2Z COMMSCOPE Order :- 308546 :-Delivered By 01/05/2020 | awaiting | awaiting | awaiting |  |  | no |  |  | chasing pratik on info
michelle | to notify | colindale | PW544895 | 2021-06-16 | FER 1 | Talk Talk POID01804612 BBCH01804613 BGP Peers 92.31.34.66 and 92.31.34.70 VLANs 1026 and 1027 | NoCp Yet (Not Planned) | awaiting(Not Done) | awaiting | awaiting | awaiting | awaiting | awaiting | awaiting |  |  | no
Michelle | to notify | colindale | PW544897 | 2021-06-22 | FER 1 | Cisco FER to be migrated is fer-cis1.l-nws BTSS POID00070015 BBCH00070014 BGP Peers 193.113.144.10 and 193.113.144.14 VLANs 1008 and 1009 Cerberus Networks Ltd POID13048895 BBCH13048893 BGP Peers 46.37.35.138 and 46.37.35.142 VLANs 1010 and 1011 | tba | tba | tba | tba | tba | tba | tba | tba | tba | tba | no
Michelle | to Notify | Manchester | PW542762 2am | 2021-06-23 | FER 3 | GAMMA BBCH15231107 +G4WMEP00000940 - WMEP00000941 CP BGP Peers 164.39.242.126 and 164.39.242.121 BBCH15231125 WMEP00000942 - WMEP00000943 CP BGP Peers 164.39.242.118 and 164.39.242.114 | formerley PW540298 | CP00VUA(Planned and Detils Provided) | 51153873/ WAVTA14F | N | WAVTA18K/ 51153876 | N | FS0483331:-Requested Delivery Date:02/10/2020 |  |  |  | yes
michelle | to notify | colindale | PW542671 Replaced with PW548299 | 2021-06-29 | FER 5 | Murphx BBCH12738625 WMEP00000720 - WMEP00000721 CP BGP PEERS 62.72.148.54 - 62.72.148.58 Sky BBCH05250252 WMEP00000512 - WMEP00000513 CP BGP Peers 90.223.197.186 - 90.223.197.190 | NoCp Yet (Not Planned Yet) | awaiting(Not Done) | awaiting | awaiting | awaiting | awaiting | awaiting | awaiting | moved from 6th jan |  | no |  |  | stores on site from previous job
| to note | Colindale | PW544878 PW542357 at 00.00 replaces 5402372 | TBA | fer 9 | MURPHX BBCH15065769 WMEP00000876-WMEP00000877 CP BGP PEERS 62.72.148.106 - 62.72.148.102 | Yes | CP00WMG/H | WAVTPC7G/ 51157418 |  | WAVTPC8H/ 51157419 | FS0485895 Already Delivered on 20/10/2020 | REPLACES PW540372 | n |  |  | yes
| to Notify | Colindale | PW542434 at 0.00 | TBA - Dan dealing | FER 7 | Cisco FER to be migrated is fer-cis7.l-nws. BT GLOBAL SERVICES (NHS-N3) POID11793877 BBCH11793876 WMEP00000546 - WMEP00000547 Virgin Media POID12261782 BBCH12261781 WMEP00000624 - WMEP00000625 Zen Internet Ltd POID13043662 BBCH13043663 WMEP00000818 - WMEP00000819 Murphx POID15026271 BBCH15026269 WMEP00000868 - WMEP00000869 | Yes | CP000XOS(Planned)But Had to Cancel the Schem on Steve Write Request for Capacity Usage.But rest all details are still in place.PFA Email | WAVUMJ4N/51164930:-PREP |  | WAVUL94N/51164563:-OOH Support |  | FS0490866 Already Delivered to Site on 24/11/2020 | n | moved from 4th Feb | cables not complete | yes |  |  | Murphx - cancelled will be done on SR2 = sky going ahead
| to notify | Faraday | PW546658 | 2021-05-25 | FER 5 | "Service impacting Change being manually notified by enterprise, contact Mark Haley for detail" Following successful completion of FOA migrations we will migrate remaining services from Cisco FER to the Nokia FER: Cisco FER to be migrated is fer-cis5.l-far Spitfire Network Services BBCH15306776 POID15306777 WMEP00000958 - WMEP00000959 BGP Peers 87.224.0.153 - 87.224.0.157 GAMMA TELECOM LIMITED BBCH13147189 POID13168445 WMEP00000842 - WMEP00000843 BGP PEERs 164.39.242.209 - 164.39.242.213 BBCH13147283 WMEP00000844 - WMEP00000845 BGP PEERS 164.39.242.217 - 164.39.242.221 BBCH13168683 WMEP00000852 - WMEP00000853 BGP PEERS 164.39.242.177 - 164.39.242.181 |  |  | PREP ESTIMATE: -WAWCPA3E |  | OOH Estimate :-WAWCPA8K | [8 empty] | Order Reference :- 311523 Delivered By 28/05/2021

## migrations superceed or done
| notify Michelle | Location | Pew and time | date | FER | notes | wfmt cp Job | WFMT ref | install job ref | Install job resourced | coop job no | Coop job Y/N | Notes | complete | moved
| Michelle | Colindale | PW542671 | 2021-02-16 | FER 5 | Murphx BBCH12738625 WMEP00000720 - WMEP00000721 CP BGP PEERS 62.72.148.54 - 62.72.148.58 Sky BBCH05250252 WMEP00000512 - WMEP00000513 CP BGP Peers 90.223.197.186 - 90.223.197.190 | NoCp Yet (Not Planned) | Not Planned Yet | NA | NA | NA | NA | NA | n | moved from 6th jan | superceeded
| to note | Colindale | PW544452 | 2017-02-23 | FER 3 | Cisco FER to be migrated is fer-cis3.l-nws Cable & Wireless UK POID04623295 BBCH04623294 WMEP00000490 - WMEP00000490 BGP Peers 87.74.20.33 - 87.74.20.37 BBCH15037651 WMEP00000878 - WMEP00000878 BGP Peers 87.74.215.45 - 87.74.20.45 Murphx POID12948106 BBCH12948105 WMEP00000794 - WMEP00000795 BGP Peers 62.72.148.78 - 62.72.148.82 Griffin POID01891861 BBCH01891860 WMEP00000458 - WMEP00000458 BGP Peers 79.121.251.222 - 79.121.251.226 Cerberus POID15361323 BBCH15361322 WMEP00000978 - WMEP00000979 BGP Peers 46.37.35.154 - 46.37.35.158 | awaiting | Not Planned Yet | awaiting | awaiting | awaiting | awaiting | awaiting | awaiting |  | superceeded
| Michelle | Colindale | PW542434 at 0.00 | 2021-01-12 | FER 7 | Cisco FER to be migrated is fer-cis7.l-nws. BT GLOBAL SERVICES (NHS-N3) POID11793877 BBCH11793876 WMEP00000546 - WMEP00000547 Virgin Media POID12261782 BBCH12261781 WMEP00000624 - WMEP00000625 Zen Internet Ltd POID13043662 BBCH13043663 WMEP00000818 - WMEP00000819 Murphx POID15026271 BBCH15026269 WMEP00000868 - WMEP00000869 | Yes | CP000XOS(Planned)But Had to Cancel the Schem on Steve Write Request for Capacity Usage.But rest all details are still in place.PFA Email | WAVUMJ4N/51164930:-PREP |  | WAVUL94N/51164563:-OOH Support |  | FS0490866 Already Delivered to Site on 24/11/2020 | n | moved from 4th Feb | cables not complete | superceded
| Michelle | colindale | PW542677 at 0.00 | 2021-02-04 | FER 4 | WAVENET BBCH15096008 WMEP00000888 - WMEP00000889 BGP Peers 195.26.38.109 - 195.26.38.105 ZEN via BBCH12837898 WMEP00000750 - WMEP00000751 BGP Peers 82.71.176.10 - 82.71.176.14 Murphx BBCH15026123 WMEP00000866 - WMEP00000867 BGP Peers 62.72.148.86 - 62.72.148.90 ICUK BBCH13032936 WMEP00000820 - WMEP00000821 BGP Peers 80.209.128.162 - 80.209.128.166 | NoCp Yet | NA(Not Planned) | NA | NA | NA | NA | NA | n | moved from 12th Jan | superceeded
| michelle | Colindale | PW543115 at 00:00 | 2021-02-12 | FER 4 | Cisco FER to be migrated is fer-cis4.l-nws WAVENET LTD BBCH15096008 POID15096010 WMEP00000888 WMEP00000889 BGP Peers 195.26.38.110 - 195.26.38.106 Zen BBCH12837898 POID12837899 WMEP00000750 WMEP00000751 BGP peers 82.71.176.9 - 82.71.176.13 | NoCp Yet | Not Planned Yet | NA | NA | NA | NA | NA | n | moved from 21 Jan | superceeded
| michelle | Colindale | PW543120 at 00:00 | 2021-02-10 | FER 4 | Cisco FER to be migrated is fer-cis2.mr-dh Murphx BBCH15026123 POID15026125 WMEP00000866 WMEP00000867 BGP Peers 62.72.148.85 - 62.72.148.89 ICUK COMPUTING SERVICES BBCH13032936 POID13040934 WMEP00000820 WMEP00000821 BGP Peers 80.209.128.161 - 80.209.128.165 | NoCp Yet | Not Planned Yet | NA | NA | NA | NA | NA | n | moved from 27 jan | superceeded
| michelle | Manchester | PW542762 | 2021-01-14 | FER 3 | was PW540298 FER 3 Manchester Timico BBCH11961589 WMEP00000582 WMEP00000583 CP BGP Peers 62.121.4.26 & 62.121.4.30 Virgin Media BBCH12261799 WMEP00000628 WMEP00000629 CP BGP Peers 62.252.192.229 & 62.252.192.233 FluidOne BBCH12480108 WMEP00000662 WMEP00000663 CP BGP Peers 89.105.100.17 & 89.105.100.21 GAMMA BBCH15231107 WMEP00000940 - WMEP00000941 CP BGP Peers 164.39.242.126 and 164.39.242.121 BBCH15231125 WMEP00000942 - WMEP00000943 CP BGP Peers 164.39.242.118 and 164.39.242.114 | formerley PW540298 | CP00VUA(Planned and Detils Provided) | 51153873/ WAVTA14F | N | WAVTA18K/ 51153876 | N | FS0483331:-Requested Delivery Date:02/10/2020 | N
YES | complete | Manchester | PW540353 | 2020-11-11 | FER 3 | GAMMA BBCH15231107 WMEP00000940 - WMEP00000941 CP BGP Peers 164.39.242.126 and 164.39.242.121 BBCH15231125 WMEP00000942 - WMEP00000943 CP BGP Peers 164.39.242.118 and 164.39.242.114 TELEFONICA O2 UK LIMITED BBCH12352949 WMEP00000634 - WMEP00000635 CP BGP Peers 46.233.123.73 and 46.233.123.77 Kingston Communications BBCH13176171 WMEP00000856 - WMEP00000857 CP BGP Peers 194.207.0.66 and 194.207.0.70 | YES | CP00VUA(Planned and Detils Provided) | FER03 NEW FER PREP CROL FOR 10G WAVTA14F/51153873 |  | OOH Support for FER 0 CROL for 10G @ Manchester WAVTA18K/ 51153876 |  |  | y
| mhelleic | colindale | PW542427 0.00 start | 2021-02-03 | FER 8 | Cisco FER to be migrated is fer-cis8.l-nws. POID12695507 BBCH12695+G12506 WMEP00000710 - WMEP00000711 BGP Peers 195.166.143.114 - 195.166.143.118 BBCH12695526 WMEP00000712 - WMEP00000713 BGP Peers 195.166.143.122 - 195.166.143.126 BBCH12695536 WMEP00000714 - WMEP00000715 BGP Peers 195.166.143.194 - 195.166.143.198 BBCH12695553 WMEP00000716 - WMEP00000717 BGP Peers 195.166.143.202 - 195.166.143.206 | Yes | CP00XFQ(Planned and Delivered) | WAVUMA5V/ 51164861:-PREP |  | WAVUEE3A/51162893:- OOH |  | Cables Been Delivered Through ASC Fast Track FS0489754 Already Delivered on 16-11-2020 | n
| COMPLETE | Colindale | PW540376 | 2020-10-29 | FER 9 | SPITFIRE NETWORK SERVICES BBCH15179786 WMEP00000892-WMEP00000893 CP BGP PEERS 87.224.0.86 - 62.133.0.250 CABLE AND WIRELESSBBCH15180306, BBCH15205567 WMEP00000898,WMEP00000899, WMEP00000902, WMEP00000903 CP BGP PEERS 87.74.215.49, 87.74.215.53, 87.74.215.57, 87.74.215.61 | Yes | CP00WMH(Planned And Delivered) | ESTIMATE WAVTRD7R/51157714 :- PREP for PREP FER9 PW540376 provide new 10G connectivity from NEW FER to COMACC |  | Estimate WAVTRD8S/51157715 :- FER9 PW540376 CROL. Plan and provide new 10G connectivity from NEW FER to COMACC tray as per linked CROL OOH PEW |  | Cables Ordered through ASC Reference FS0486122:-Delivered on 22/10/2020 | y
| COMPLETE | Colindale | PW540377 | 2020-11-04 | FER 9 | PLUSNET BBCH12153092 , BBCH12153100 , BBCH12153103 , BBCH12153117 WMEP00000600, WMEP00000601, WMEP00000602, WMEP00000603, WMEP00000604, WMEP00000605, WMEP00000606, WMEP00000607 CP BGP PEERS 195.166.143.82, 195.166.143.86, 195.166.143.90, 195.166.143.94, 195.166.143.98, 195.166.143.102, 195.166.143.106, 195.166.143.110 | Yes | Cp00WMI(Planned And Delivered) | Estimate WAVTPA2X/51157398 For PRE-CABLING PREP FOR FER Replacement Cisco FER9 to Nokia 10G PW540377 :- PREP for PREP FER9 PW540376 provide new 10G connectivity from NEW FER to COMACC |  | Estimate WAVTPA3Y/ 51157400 FER9 PW540377 CROL. Plan and provide new 10G connectivity from NEW FER to COMACC tray as per linked CROL OOH PEW :- FER9 PW540376 CROL. Plan and provide new 10G connectivity from NEW FER to COMACC tray as per linked CROL OOH PEW | gifford, Derek | Cables Ordered through ASC Reference FS0485889:-Delivered on 20/10/2020 | Y
| COMPLETE | Faraday | PW540789 | 2020-11-06 | fer 1 | CP test Migration POID00117715 WMEP00000282 WMEP00000283 | Yes | CP00VUE(Planned And Delivered) | 51153581 /WAVT906C | yes | 51153588 /WAVT912A |  |  | Y
| replaced | Manchester | PW540297 | 2020-11-17 | FER 2 | PW540297 01/10/2020 TELEFONICA O2 UK LIMITED BBCH12959825 WMEP00000808 WMEP00000809 CP BGP Peers 46.233.123.89 & 46.233.123.93 Redcentric BBCH13140037 WMEP00000824 WMEP00000825 CP BGP Peers 178.250.99.114 & 178.250.99.118 ZEN BBCH01481727 WMEP00000384 WMEP00000385 CP BGP Peers 82.71.176.65 & 82.71.176.69 | yes | CP00VOI | zen WAVT6H1Z/51152881 confirmed cabled |  | Zen WAVT6H4C/51152885 |  | FS0482569:-Requested Delivery Date:30/09/2020 | replaced
| complete | Manchester | PW540358 | 2020-11-25 | FER 1 | CIVICA UK LTD BBCH01654915 WMEP00000406- WMEP00000407 CP BGP PEERS 213.143.129.106- 213.143.129.110 HOMEGROUP LTD BBCH01921261 WMEP00000482-WMEP00000483 CP BGP PEERS 185.8.88.2-185.8.88.6 SSE TELECOMS BBCH01919093 WMEP00000484-WMEP00000485 CP BGP PEERS 161.12.15.138-161.12.15.142 UPDATA INFRASTRUCTURE LTD BBCH12008789 WMEP00000574-WMEP00000575 CP BGP PEERS 46.183.199.182-46.183.199.226 | yes | CP00TF9(Planned and Delivered) | 51153359/ WAVT872K /51153359 Prep- work/ 51157419 Fast Track Cable Reference :-FS0484820 :-Delivered on 13/10/2020:-All cables Delivered Except One as Stores Not Available Replacement is in WAY order 294219 will ship to Magna Park on the 17th November | asked | WAVT873L / |  | partial | Y
| replaced | Manchester | PW540354 replaced by 543662 | 2020-12-04 | FER 1 | GAMMA TELECOM LIMITED BBCH13147967 WMEP00000826 - WMEP00000827 CP BGP Peers 164.39.242.226 and 164.39.242.230 BBCH13144345 WMEP00000828 - WMEP00000829 CP BGP Peers 164.39.242.234 - 164.39.242.238 BBCH13144547 WMEP00000830 - WMEP00000831 CP BGP Peers 164.39.242.242 and 164.39.242.246 BBCH13144563 WMEP00000832 - WMEP00000833 CP BGP Peers 164.39.242.250 and 164.39.242.254 | YES | CP00TF8 | WAVR5L6B ​ Cabled previously |  | WAVR5L7C |  | FS0477106 Delivered on 20/08/2020 | replaced
| Michelle | Manchester | PW543662 at 00.00 replaces PW540354 | 44202 | FER 1 | GAMMA TELECOM LIMITED BBCH13147967 WMEP00000826 - WMEP00000827 CP BGP Peers 164.39.242.226 and 164.39.242.230 BBCH13144345 WMEP00000828 - WMEP00000829 CP BGP Peers 164.39.242.234 - 164.39.242.238 BBCH13144547 WMEP00000830 - WMEP00000831 CP BGP Peers 164.39.242.242 and 164.39.242.246 BBCH13144563 WMEP00000832 - WMEP00000833 CP BGP Peers 164.39.242.250 and 164.39.242.254 |  | CP00TF8(Planned and Delivered) | WAVR5L6B ​ Cabled previously |  | WAVR5L7C |  | FS0477106 Delivered on 20/08/2020 |  | moved from 16th Feb | Failed
| michelle | Manchester | PW540355 at 0.00 | 2021-01-13 | FER 1 | UKS LTD BBCH12506226 WMEP00000674 - WMEP00000675 CP BGP PEERS 62.149.53.78 - 62.149.53.82 Odyssey Systems Ltd BBCH00028151 WMEP00000056 - WMEP00000057 CP BGP Peer 92.42.127.1 - 92.42.127.5 Talk Internet Ltd BBCH00029592 WMEP00000058 - WMEP00000059 CP BGP Peers 92.42.120.129 - 92.42.120.133 BISTECH LIMITED BBCH15326388 WMEP00000972 - WMEP00000973 CP BGP Peers 82.113.237.58 - 82.113.237.62 | yes | CP00TF9(Planned and Delivered) | 51153359/ WAVT872K | asked | WAVT873L / |  | multiple connections only two blanks - having issues | n | partial | partial
| michelle | Manchester | PW543013 at 00:00 | 2021-01-20 | FER 2 | Cisco FER to be migrated is fer-cis2.mr-dh replaces PW540297 01/10/2020 TELEFONICA O2 UK LIMITED BBCH12959825 WMEP00000808 WMEP00000809 CP BGP Peers 46.233.123.89 & 46.233.123.93 Redcentric BBCH13140037 WMEP00000824 WMEP00000825 CP BGP Peers 178.250.99.114 & 178.250.99.118 | Yes | CP00VOI(Planned And Delivered) | zen WAVT6H1Z/51152881 confirmed cabled |  | Zen WAVT6H4C/51152885 | failed cables | FS0482569:-Requested Delivery Date:30/09/2020 | N
| michelle | Colindale | PW542357 at 00.00 replaces 5402372 | 2021-01-21 | FER 9 | MURPHX BBCH15065769 WMEP00000876-WMEP00000877 CP BGP PEERS 62.72.148.106 - 62.72.148.102 | Yes | CP00WMG(Planned And Delivered) | WAVTPC7G/ 51157418 |  | WAVTPC8H/ 51157419 | FS0485895 Already Delivered on 20/10/2020 | REPLACES PW540372 | n | moved from 10th Feb | failed
| Michelle | Manchester | PW542418 at 00.00 | 2021-01-27 | FER 1 | REDCENTRIC BBCH00066916, BBCH12893083, BBCH12957436 WMEP00000200,WMEP00000201,WMEP00000782,WMEP00000783,WMEP00000800,WMEP00000801 CP BGP PEERS 188.95.133.238, 188.95.135.2, 85.118.1.86, 85.118.1.94, 178.250.99.97, 178.250.99.101 | Yes | CP00TF9(Planned and Delivered) | NIMS Estimate WAVT872K /51153359 Prep- work/ 51157419 Fast Track Cable Reference :-FS0484820 :-Delivered on 13/10/2020:-All cables Delivered Except One as Stores Not Available Replacement is in WAY order 294219 will ship to Magna Park on the 17th November | asked | WAVT873L / 51153360 |  |  | n | moved from 10 Feb | superceeded
| michelle | Manchester | PW540356 00:00 | 2021-01-28 | FER 1 | CONVERGENCE BBCH15317660 WMEP00000968- WMEP00000969 CP BGP PEERS 88.151.222.17- 88.151.222.21 EXPONENTIAL-E LTD BBCH12654178 WMEP00000694-WMEP00000695 CP BGP PEERS 5.148.70.194- 5.148.70.198 REDCENTRIC BBCH00066916, BBCH12893083, BBCH12957436 WMEP00000200,WMEP00000201,WMEP00000782,WMEP00000783,WMEP00000800,WMEP00000801 CP BGP PEERS 188.95.133.238, 188.95.135.2, 85.118.1.86, 85.118.1.94, 178.250.99.97, 178.250.99.101 BTSS(CWS LTD) BBCH00060766 WMEP00000190-WMEP00000191 CP BGP PEERS 193.113.144.2-193.113.144.6 INTEC PLC Can't find the BBCH or WMEP refs CP BGP PEERS 188.95.133.238-188.95.135.2 | yes | CP00TF9(Planned And Delivered) | 51153359/ WAVT872K /51153359 Prep- work/ 51157419 Fast Track Cable Reference :-FS0484820 :-Delivered on 13/10/2020:-All cables Delivered Except One as Stores Not Available Replacement is in WAY order 294219 will ship to Magna Park on the 17th November | asked | WAVT873L / |  |  | n |  | superceeded
| Michelle | Colindale | PW542641 at 0.00 | 2021-02-09 | fer 6 | GAMMA POID13168483 BBCA13168483 BBCH13147633 WMEP00000850 - WMEP00000851 vlan1008 ip address 164.39.242.202 vlan1009 ip address 164.39.242.206 BBCH13147819 WMEP00000848 - WMEP00000849 vlan1012 ip address 164.39.242.194 vlan1013 ip address 164.39.242.198 BBCH13144547 WMEP00000830 - WMEP00000831 vlan1014 ip address 164.39.242.186 vlan1015 ip address 164.39.242.190 BBCH13144563 WMEP00000832 - WMEP00000833 vlan1138 ip address 164.39.242.174 vlan1139 ip address 164.39.242.170 | Yes | CP00XS0(Planned)But Had to Cancel the Schem on Steve Write Request for Capacity Usage.But rest all details are still in place.PFA Email | WAVUR22R/ 51165628 Cables Been Fast Tracked through FS0491552:-Requested Delivery Date:30/11/ |  | WAVUR27W/ 51165633 |  |  | N
| to note | Manchester | PL781 - PW540356 | 2021-04-14 | fer 1 | Cisco FER to be migrated is fer-cis1.mr-dh. Convergence and Exponential built on FER CONVERGENCE BBCH15317660 WMEP00000968- WMEP00000969 CP BGP PEERS 88.151.222.17- 88.151.222.21 EXPONENTIAL-E LTD BBCH12654178 WMEP00000694-WMEP00000695 CP BGP PEERS 5.148.70.194- 5.148.70.198 REDCENTRIC – moved to 26/11/2020 BBCH00066916, BBCH12893083, BBCH12957436 WMEP00000200,WMEP00000201,WMEP00000782,WMEP00000783,WMEP00000800,WMEP00000801 CP BGP PEERS 188.95.133.238, 188.95.135.2, 85.118.1.86, 85.118.1.94, 178.250.99.97, 178.250.99.101 BTSS(CWS LTD) BBCH00060766 WMEP00000190-WMEP00000191 CP BGP PEERS 193.113.144.2-193.113.144.6 | yes | CP00TF9 | 51153359/ WAVT872K /51153359 Prep- work/ 51157419 Fast Track Cable Reference :-FS0484820 :-Delivered on 13/10/2020:-All cables Delivered Except One as Stores Not Available Replacement is in WAY order 294219 will ship to Magna Park on the 17th November | asked | WAVT873L / | [5 empty] | yes | complewte
| to note | Manchester | PW544877 | 2021-04-15 | fer2 | Following successful completion of FOA migrations we will migrate remaining services from Cisco FER to the Nokia FER: Cisco FER to be migrated is fer-cis2.mr-dh PW540297 01/10/2020 TELEFONICA O2 UK LIMITED BBCH12959825 WMEP00000808 WMEP00000809 CP BGP Peers 46.233.123.89 & 46.233.123.93 Redcentric BBCH13140037 WMEP00000824 WMEP00000825 CP BGP Peers 178.250.99.114 & 178.250.99.118 |  | CP00VOI(Planned And Delivered) | zen WAVT6H1Z/51152881 confirmed cabled |  | Zen WAVT6H4C/51152885 | failed cables | FS0482569:-Requested Delivery Date:30/09/2020 |  |  |  | yes | complete
| to notify | colindale | PW542427 | 2021-05-12 | fer 8 | Service impacting Change being manually notified by enterprise, contact Mark Haley for detail" Following successful completion of FOA migrations we will migrate remaining services from Cisco FER to the Nokia FER: Cisco FER to be migrated is fer-cis8.l-nws. PLUSNET POID12695507 BBCH12695506 WMEP00000710 - WMEP00000711 BGP Peers 195.166.143.114 - 195.166.143.118 BBCH12695526 WMEP00000712 - WMEP00000713 BGP Peers 195.166.143.122 - 195.166.143.126 BBCH12695536 WMEP00000714 - WMEP00000715 BGP Peers 195.166.143.194 - 195.166.143.198 BBCH12695553 WMEP00000716 - WMEP00000717 BGP Peers 195.166.143.202 - 195.166.143.206 | Yes | CP00XFQ(Planned and Delivered) | WAVUMA5V/ 51164861:-PREP |  | WAVUEE3A/51162893:- OOH |  | Cables Been Delivered Through ASC Fast Track FS0489754 Already Delivered on 16-11-2020 | n |  |  | cancelled
| to note | Manchester | PW542418 | cancelled | fer 1 | REDCENTRIC BBCH00066916, BBCH12893083, BBCH12957436 WMEP00000200,WMEP00000201,WMEP00000782,WMEP00000783,WMEP00000800,WMEP00000801 CP BGP PEERS 188.95.133.238, 188.95.135.2, 85.118.1.86, 85.118.1.94, 178.250.99.97, 178.250.99.101 | yes | CP00TF9 | 51153359/ WAVT872K /51153359 Prep- work/ 51157419 Fast Track Cable Reference :-FS0484820 :-Delivered on 13/10/2020:-All cables Delivered Except One as Stores Not Available Replacement is in WAY order 294219 will ship to Magna Park on the 17th November | asked | WAVT873L / | need to raise |  |  |  |  | yes | PW542418 Cancelled – Redcentric circuits down on FER 1. Migration not needed, not possible while down on cisco FER